## Slide 1
Audit Superintendent, DLFA
Sri Satya Bhusan Mishra

## Slide 2
AUDIT OF WORKS, INCLUDING
WORKS THROUGH TENDER PROCESS

## Slide 3: Public Works
Public Works means any civil works, public health engineering works, irrigation, embankment and drainage works and electricity works. The Odisha Public Works Department(OPWD)Code is intended to define the scope of function of the Officers in-charge of Public works working under the Administrative Control of different department such as Works, Water Resources, H & U.D., Rural Development, and Panchayati Raj to which the execution of public works is assigned by the State Government.
To understand the work of an organisation, it is essential to know the Organisational structure of that department.
The typical organisational structure of an Engineering Department which is taking of public works i.e. Creation & maintenance of assets.

## Slide 4
E.I.C.
Chief Engineer
Superintendent Engineer
Executive Engineer
Dy. Executive Engineer / Asst. Executive Engineer
Asst. Engineer / Junior Engineer
The O.P.W.D. Code while defining the procedure to be adopted for the work also indicates the financial power of different officers of the Engineering Department.
Though, the O.P.W.D. Code is followed for execution of works in P.R. Department, the financial power is different from that which is as per the Administrative Orders issued by the Department from time to time.

## Slide 5
The work starts which is conceptualisation followed by planning, estimation, selection of agency, award of work, billing, checking of bill, which ends with payment.
In P.R. Department particularly for the Panchayat works this conceptualisation starts with Palli Sabha / Grama Sabha which decides on the projects to be taken up during a year and amount allocation with selection of agency i.e. V.L.L. (Village Level Leader)
This V.L.L. can be one or more than that depending on the number of works to be taken up, as one V.L.L. cannot be engaged for more than three works.
The Palli Sabha / Grama Sabha constitutes with the number of voters in that particular area, which should be attended by minimum 1/3rd to fulfil the criteria of the quorum.

## Slide 6
If, the Sabha fails to have quorum in the second seating also then the work can be taken up departmentally.
With selection of the project finally approved & assigned to a scheme, the P.E.O. (Panchayat Executive Officer) opens a file for each work and request the Junior Engineer / G.P.T.A (Gram Panchayat Technical Assistant) to prepare an estimate.
For preparing an estimate, the concerned officer has to frame the same, basing on the procedure as detailed in the O.P.W.D. Code.

## Slide 7
The requirements for execution of a work are :
  Selection of Sites.
  Broad scope of work.
  Specification to be followed.
  Analysis of rates is to followed to derive the rates
  Inclusion of O.H. Charges / contractor profit in the estimate (in case of tender works).
  Prevailing Schedule of Rates to be followed.
  Quarry / Crusher site (Carriage / Lead)

## Slide 8
Types of Works in PRIs & ULBs- The public works in PRIs & ULBs are generally
1. CC Roads,
2. Bituminous Roads
3. New Earthen Roads, Metal-Morrum Roads in MGNREGA Scheme
4. Buildings (Community Centers, School Buildings, G.P. Office Buildings, Awanganbadi Kendras, Crematorium, Bathing Ghats with rest Shed)
5. Boundary Walls
6. Digging of Tube Wells and Construction of Tube Well Platforms

## Slide 9: Some Key Words/ Facts of Works Audit
After the approval of Projects by the District Administration under different Schemes, the projects to be enlisted in the Work cum project register of the PRI and ULB. The work order is to be issued to the executant (Other than Contract Work) on basis of the VLL (Village level Worker ) selected by the Paallisabha/ Gramsabha of different Gram Panchayat.Gram Sabha hold meetings normally 2 to 4 times a year, but can meet as and when necessary.The works under PRI institutions with estimate upto 10(Ten) lakhs is to be executed through departmentally. The work order issued to the executant, only after preparation of the DPR, detailed sketch/drawing of the project and estimate by the JE. In the work order the time stipulation for completion of the project is to be mentioned and accordingly an agreement is to be made with the executant by the order issuing official.

## Slide 10: 1. Preparation of Detailed Project Report (DPR)
The JE concerned is to prepare a detailed project report like feasibility of the project, how the project is beneficial to the general public, report regarding adaptation of different items of work with current Schedule of rates, analysis of rates. The Junior Engineer of the Panchayat Samiti shall give a certificate as under, ''Certified that I have personally visited the spot and prepared the estimate using the sanctioned Schedule of rates and providing for the most economical and safe way of executing the work.

## Slide 11: 2. Schedule of Rates-
The Works Deptt., Govt. of Odisha from time to time publish the rates of items of different building materials along with labour, conveyance of building materials along with other misc. items. The last SR was published vide Works Deptt. Office memorandum No.13827/Dt. 16.09.2017, effective from 1st July-2017 after implementation of GST. The revised rate of Labour (Unskilled- 326, Semi-Skilled-366, Skilled-416, Highly Skilled-476) was effective from 01.04.2022.

## Slide 12: 3. Analysis of Rates-
The analysis of Rates arrived from the Analysis of rate fixed by Govt. of Odisha. The final analysis of an item work includes the basic rate from SR-2014 (Effective from the year-2017, effective after implementation of GST)+ rate of Conveyance + Rate of Labour+ Royalty)

## Slide 13: 4. Lead Statement-
The distance from the approved quarry from the work site is referred as lead. The lead statement has to be prepared basing on actual distance approved by the District Authority and approved conveyance rate as prescribed by Schedule of Rates issued from time to time by Works Deptt.

## Slide 14
Works

## Slide 15
CC Road

## Slide 16: The formulation of an estimate has to be followed with Technical sanction.
Technical sanction is the approval accorded by an Engineer certifying that the estimate that has been framed for the work has taken all engineering requirements into consideration including safety provisions to have the structure technically sound.
In P.R. Department the technical sanction power is vested as below. (G.O. No.403/PR, Dt.31.08.2010)
Junior Engineer up to 3.00 Lakhs
Asst. Executive Engineer above 3.00 lakh up to 6.00 lakh
Executive Engineer (APD Technical) above 6.00 lakh

## Slide 17
Administrative approval is accorded by the officials as per the delegation of financial powers by the finance department from time to time.
In P.R. Department the Administrative approval power is vested as below.
Block Development Officer . . Up to Rs. 10.00 lakh
Chairman of Panchayat Samiti . . Above Rs. 10.00 lakh up to Rs. 15.00 lakh
Collector of the District . . Above Rs. 15.00 lakh

## Slide 18
After Technical Sanction and Administrative Approval the work has to be taken up either by the V.L.L., or Departmentally or through tender process under the supervision of the concerned Junior Engineer / G.P.T.A who will subsequently record the measurement in the M.B. In a departmental work, if the work order was issued in name of one J.E (executantant for the work), the measurement of the said work should be done by other J.E.

## Slide 19
Check Measurement:
The Assistant Engineer shall check-measure every work in respect of which he has accorded technical sanction. The Executive Engineer shall check-measure at least 10% of works, the estimates of which have been technically sanctioned by the Assistant Engineer. The Executive Engineer shall also check-measure not less than 10% of every work, the estimate of which has been technically sanctioned by him.

## Slide 20: Important points to watch during scrutiny of bills :
  Bills are in proper form & submitted in duplicate,
  Name of work, Name of agency, reference to agreement / supply order No, Serial No. of bill, reference to previous payment etc. are indicated.
  Item of work, Quantity, Unit, Rate as per agreement / Order are indicated.
  Value of work since correctly worked out.
  Advance payment / Secured Advance correctly worked out.

## Slide 21
  Details of recovery noted.
  Materials statement showing up to date issues, consumptions, recoveries is enclosed in case of Departmental materials issued to work.
  Royalty recoverable as per consumption of minor minerals correctly worked out.
  Quantities & amount as entered in the measurement book agree with the quantities & amount executed in the bill

## Slide 22: Category of Works-
1. Major Work - means an original work, the -estimated cost of which is Rs. 1, 00,000 or above.
2. Minor Work - means an original work, the estimated cost of which is over Rs. 10,000 but less than Rs. 1,00,000.
3. Petty Work - means on original work, the estimated cost which is Rs. 10,000 or less. (Substituted by Works Deptt. No. 22791 Dt. 18.08.1984)

## Slide 23: Records to be seen in Works Audit through tender Process
Sanctioned estimate;
Administrative approval;
Expenditure sanction-Allotment vis-à-vis expenditure;
Cash Book;
Counter foil of Cheques;
Agreements;
Tender documents and Detailed Tender Call Notice;
Tender call and opening registers;

## Slide 24
9. Comparative statement with correspondence file of tender;
10. Tender approval/acceptance letter;
11. Works order;
12. Register of works;
13. Vouchers including running and final payment vouchers;
14. Measurement Books, level Books, graph sheets;
15. Quality control test reports;
16. Work completion report

## Slide 25: Sequence of activities involved in execution of works Audit
Administrative approval
1. Financial Sanction
2. Technical Sanction
3. Detailed estimate
4. Bid document
5. Bidding process
i)Notice Inviting Tenders
ii)Evaluation of Bids
iii) Acceptance of Bids

## Slide 26
6. Execution of contract
i)Prescribed form
ii) Adoption of standard clauses
iii) Bill of quantities
iv) Cost and time of completion
v) Standard specification
7. Implementation of the contract
i) Measurements/check measurement
ii)Running payments
iii) Final payment
iv)Performance securities, taxes, royalties

## Slide 27
Administrative Approval: Based on the preliminary estimate framed and countersigned by the authority competent to accord technical sanction, Administrative approval is accorded for execution of the work, as per the delegation of financial powers by the finance department from time to time.
Technical Sanction: Detailed estimate based on drawings and designs is prepared for each individual work except for repairs for which lump sum provisions are sanctioned. This detailed estimate is to be sanctioned by the competent authority according to the powers delegated by the finance department of the concerned State.

## Slide 28
Additional Performance Security (APS): When the bid amount is up to 10% less than the estimated cost, no additional performance security (APS)is required to be deposited. when the bid amount is less than the estimated cost by more than 10% and within 15%, in such an event, the successful bidder will deposit the additional performance security to the extent of 1.5 times of the differential cost of the bid amount and 90% of the estimated cost. (Vide O.M. 5288/W, Dt. 04.05.2016) AMENDMENT-2017“Additional Performance Security shall be obtained from the bidder when the bid amount is less than estimated cost put to tender. In such an event, only the successful bidder who has quoted less bid price / rates than the estimated cost put to tender shall have to furnish the exact amount of differential cost i.e. estimated cost put to tender minus the quoted amount as Additional Performance Security (APS) in shape of Demand Draft / Term Deposit Receipt pledged in favour of the DDO of the office within Seven days, otherwise the bid shall be cancelled and the EMD shall be forfeited. Further, proceeding for blacklisting shall be initiated against bidder.”

## Slide 29
1) This amendment shall take effect from 24th July, 2017. 2) The Works Department Office Memorandum No.- 5288 / W, Dt.- 04.05.2016. (Annexure- I-A) stands modified accordingly pursuant to the judgment dated 27.07.2017 of the Hon’ble of High Court of Odisha. 3) This has been concurred in by the Law Department and Finance Department vide their UOR No.- 1668 / L , Dt.- 19.08.2017 and UOR No.- 56-WF-I, Dt.- 24.08.2017 respectively. (No.- 14299 / W Dt. 03.10.2017)

## Slide 30
For availing incentive clause in any project which is completed before the stipulated date of completion, subject to other stipulations it is mandatory on the part of the concerned Executive Engineer to report the actual date of completion of the project as soon as possible through fax or e-mail so that the report is received within 7 days of such completion by the concerned SE, CE & the Administrative Department. The incentive for timely completion should be on a graduated scale of one percent to 10 percent of the contract value. Assessment of incentives may be worked out for earlier completion of work in all respect in the following scale:

## Slide 31
Before 30% of contract period =10% of Contract Value
Before 20 to 30% of contract period=7.S% of Contract Value
Before 10 to 20% of contract period=5% of Contract Value
Before 5 to 10% of contract period=2.5% of Contract Value
Before 5% of contract period=1% of Contract Value (Vide O.M. No.- 5288/W, Dt. 04.05.2016)

## Slide 32
CODAL PROVISION FOR TENDERS { VIDE OPWD CODE-3.5.9}[Subject to the provision contained in Appendix-XXXIII to the OPWD Code Vol. II] Tenders should invariably be invited publicly in the manner prescribed in Appendix IX to the Code and in paragraph 3-5-10 below for all works given out on, contracts and estimated to cost above Rs 5 lakh except in cases where additional works or items of work have to be undertaken as part of a scheme work for which tenders have originally been invited publicly and which are required to be executed while the work originally undertaken is in progress or for other exceptional reasons. (Substituted vide file no.- 10147/W, Dt.- 31.08.2015)

## Slide 33
Notes: (I) Contract for works estimated to cost up to Rs. 5 lakh may be given out with or without invitation of open tenders at the discretion of the Divisional Officers to the best advantage of Government. All other provisions remain unaltered. (Substituted vide file no.- 10147/W, Dt.- 31.08.2015) (II) The advertisement charges relating exclusively to a particular work may be debited to the head 'works contingencies' of the concerned work; when such charges are common to several works the same may, be debited to 'office expenses'.

## Slide 34
(III) If a work is to be split up for facility of execution, the approval of the authority competent to accept the tender for the work as a whole should be obtained before inviting tenders for the work. (See Para 3-5-24). (IV) Unless otherwise authorised by competent authority no tender shall be invited and accepted for a work to which administrative approval and technical sanction has not been accorded. (See exception to para 3-7-1).

## Slide 35
Revised administrative approval and revised technical sanction to be obtained where expenditure exceeded 15 per cent of the original approval.
►The technical sanction has been accorded based on adequate technical data obtained after detailed pre-construction survey and investigation.
Schedule of Rates (SoR)/ Analysis of Rates
►To facilitate the preparation of estimates under Public Works, Government issues a standard SoR along with their standard data and rate analysis. The SR is approved by the Rate Board on the basis of prevailing rates of various materials and labour fixed under the Minimum Wages Act.
► The SoR is the primary instrument in Works Audit since it is used for the important purpose of preparing estimates and also used as a guide in settling rates in contracts.

## Slide 36
► The SoR provides various chapters consisting of rates of materials, rates of labour, rates for conveyance of materials, different items of construction works etc. It also indicates the extra rate if any to be allowed over and above the SR and circumstances thereof. Audit check
► The SoR has been approved by the Rate Board, concurred in Finance Department and notified in the Gazette.
►The rates entered in the estimate should generally agree with the SoR.
►The overhead charges (@7.5%) and Contractor’s profit (@7.5%) over the basic rate of materials and labour to be correctly provided.
► Rates of labour provided were as per the minimum Wages Act.

## Slide 37
► Lead charges have been provided correctly in the analysis of item rates.
► Inclusion of unwarranted items in the analysis, may be checked.
► Hire charge of machinery and equipments are correctly provided.
► T&P, sundries, supervision charges etc. have been included at the prescribed rates.
► Data have been adopted correctly to arrive at unit rate.
► In case of revised SR, the same is to be compared with the previous SR to ascertain the inclusion/ provision of new items.
► Taxes, Royalties, etc. to be correctly taken in the analysis of rate of the work.

## Slide 38: Estimates -
► Estimates are of two types viz. lump sum and item rates. Lump sum estimate is prepared in lump provision basis for initial approval. The item rate estimate indicates the estimated cost of different items based on the approved plan and designs for the project/work.
The estimate should be comprehensive and indicate
(i) History of the proposal,
(ii) Design adopted,
(iii) Scope of execution,
(iv) Rates adopted,
(v) Total cost of the work/project,

## Slide 39
(vi) Whether lump-sum or item rate,
(vii) Inclusion of establishment charges,
(viii) Availability of construction plant, machinery and materials and land,
(ix) Time schedule for completion
(x) Provisions for overheads.

## Slide 40: Audit checking Procress
► Provisions in the estimates are as per the approved plan/design.
►The estimate is supported by a techno-economic-cum-feasibility study to indicate that the best site has been adopted.
►A group of works which forms one project is considered as one work for obtaining sanction of competent authority. In case, a single work has been splitted into small reaches/units, the urgency for such split up and its approval by competent authority should be examined.
► Rates under different items matched with the approved Schedule of Rates (SR). The rates of non-scheduled items are based on field survey reports and prevailing market rates.

## Slide 41
►The validity and reality of the SR may be examined. The basic rates, materials cost, contractor's profit (over-head charges), sundries, T & P charges and different labour rates adopted in the SR compares with approved Government rates.
►The location of departmental quarries may be examined to verify the adoption of shortest and direct lead in the estimate for obtaining construction materials.
► Adequacy of the pre-construction surveys may be examined with reference to the modifications/deviations that occur during actual execution.
►The competency of the authority according technical sanction may be examined with reference to the delegation of powers. Bid Document, bidding process and evaluation of bids

## Slide 42
►Bid document comprise Notice Inviting Tender (NIT), the form of tender to be used along with a set of conditions, the schedule of quantities of work (bill of quantities) and drawings and specifications those are to be followed during execution of the work. These documents are to be kept ready before invitation of the bids.
► Competency of the authority sanctioning the bid document.
► Bill of quantities (BOQ) compares with the estimated provisions.
►All the essential documents are annexed to the bid document.
► NIT stipulates the total estimated cost and time required for completion.

## Slide 43
► The NIT floated is transparent and widely published in local/national dailies according to the money value of the work.
► Lead time for submission of the bid is as per prescribed time limit.
► Accounting of the bid documents and its sale proceeds, has been done properly and promptly.
► Tenders are opened in presence of intending contractors or their representatives and entered in the register.
► The Divisional Accountants Officer / Divisional Accountant/ Accounts Officer of ULB5 is present during opening of the tenders and has signed as a token of his presence
► No irrational rate quoted by the bidders.

## Slide 44
► Negotiations are carried out with the bidders towards reduction of high rates and withdrawal of special conditions.
► Prescribed time frame for disposal/acceptance of the tenders is adhered to. If not, the financial implication and the reasons for delay in acceptance to be examined.
Acceptance of the Bids
►Normally, lowest responsive bid should be accepted within 90 days of its receipt keeping in view the criteria prescribed in the NIT. For acceptance of bid other than the lowest, the justification for the same has to be kept on record. The power of acceptance of tender is the same as per the sanction of estimate by EIC/CE/SE/EE. Tenders for supply/works for more than Rs.5.00 crore should be refered to Administrative Department for finalisation where there is Engineer-in-Chief. Where there is no EIC, tenders above Rs.2.00 crore should be referred to Administrative Department.

## Slide 45
► Competency of the authority approving/accepting a bid.
► Match the amount of the approved/accepted bid with that mentioned in the bid document and comparative statement. Discrepancy if any, may be investigated.
►The letter of acceptance of the tender has been communicated in the prescribed form to the bidder within the validity period of the bid.
►Earnest money (EMD)deposited by each bidder.
► Plan, estimates and designs are approved by the department prior to allotment of the of work.
► Administration approval, Technical and Financial Sanctions have been accorded.
► Work has been allowed after execution of agreement indicating cost of the works and period of completion etc.

## Slide 46: Contracts:
► Contract is an agreement executed between two parties enforceable by law. Contracts are broadly categorized as (i) works contracts, (ii) supply contracts, and (iii) service contracts. The agreements are to be executed in standard form indicating accepted/approved cost, items of work and quantities to be executed and time approved for completion of the work.

## Slide 47
►Works Contracts: Works contracts are four types: (i) lump sum contract, (ii) item rate contract, (iii) supply contract,(iv) job (piece rate) contract.
(i) In lump-sum contract, the contractor agrees to execute a work providing for all its contingencies at a fixed sum. The billing against such a contract is made on percentage basis keeping in view the overall progress and value.
(ii) Under item rate contract, the contractor executes different components of the works at agreed rates. Payments are made to him depending on the quantities and qualities of work actually done and materials supplied by the department.
(iii) Piece work (job) contracts are those executed under certain emergent situations at rates prescribed in the Schedule of Rates (SR).

## Slide 48
►Extension of time: The authority who accepted the tender can grant extension of time up to the period equivalent to that originally stipulated and for grant of extension of time limit, the matter should be submitted to next authority. Justification for grant of extension of time and competency for grant of extension of time be linked with levy of penalty and avoidable payments on escalation dues.
►Delay/Default in execution: There is provision for Penalty to be imposed in case of delay/default in execution attributed to the contractor.
►Substandard execution of work: Works are to be executed with reference to the specifications. Entries in the Site Order Book and notices issued on defective /substandard execution should be checked to substantiate rectification of defects by the contractor or rejection of the work. Payments for substandard execution have been regulated as per terms of contract

## Slide 49
►Issue of materials to contractors: Issue rates fixed are not less than the market rate. Issue rates are adopted in the estimate and mentioned in the NIT for recovery of the cost of materials from the contractors. Materials are to be issued to the Contractor on synchronization with the progress of work. Compare the issue of materials with the standard requirement for items of work and their accounting. Excess issue of materials may be ascertained from the materials consumption statement attached to each RA Bill. Recovery of cost of materials and that surplus and unused materials, which have received back, penal cost is to berealised.

## Slide 50
►Issue of materials not stipulated in the agreement. Materials are issued with approval of the competent authority indicating place of delivery and rate of recovery. The rates charged are that provided in the analysis of rate plus or minus the premia quoted. No carriage or incidental charges are allowed. In case of non-scheduled items, the rates are fixed as per codal provisions.
►Issue of Tools & Plant: Recovery of hire charges for the working hours of the plant and machinery should be checked. The progress of work is synchronised in such manner that tools & plant do not remain idle and optimum out turn is obtained.

## Slide 51
►Payment of minimum wages: Proper certificates are furnished by contractors/Engineers-in-Charge towards payment of fair wages.
►Supervision, Inspection and quality control measures: Deficiencies in execution as mentioned in the inspection notes and quality control test reports be co-related with the actual payments made to the contractors and action taken for rectification of the defects. The progress of work be examined with the work programme to ascertain cost/time over run.
►Payments for cost escalations: Payments/refunds be compared with reference to prescribed provisions, formulae, price index and work programme. No escalation cost is to be paid to the Contractor, as there was already an agreement made with him.

## Slide 52
►Warranty against works: Recovery of performance securities at the prescribed rates to ensure the warranty for rectification of works.
► Measurement: Measurements are recorded in prescribed Measurement Book (MB). The measurement indicates the name of the work, name of the agency, Agreement No. and date of commencement, stipulated date of completion, actual date of completion, date of measurement, date of check measurement, name of the officer recording the measurement and conducting the check measurements. Correctness of the quantities arrived at under various items, Recovery/non-recovery/short recovery of cost of material issued by the departmental and salvaged during execution are to be checked. In respect of Lump Sum Contract, match the percentages billing schedule adopted for payments with that provided in the contract data. Certificate of adherence to specification and acceptance of the measurements by the contractor is to be furnished.

## Slide 53
►Payment: The quantity arrived at in measurement is correctly included in the bill and the amount payable worked out as per the contract rates and no excess payment is made. Accuracy in arithmetical calculations to be checked. The extra/substituted items are paid with due approval of competent authority. Mobilisation and Machinery advances are made as per provisions in the contract/rules and that secured advances are paid against materials actually brought to site and measured. Memorandum of payments is complete and recoveries on account of materials, taxes, royalty, attachments, securities, hire-charges and others effected.

## Slide 54
►Final payments: Progressive quantities under different items do not exceed the sanctioned quantities or approved deviation and work completed during assigned period or approved extension of time. Work completion certificate is to be submitted. The ledger accounts are to be balanced to ensure all recoveries. The payment is accepted by the agency in full and final settlement of all claims.
►Refund of securities: Securities are recovered at prescribed rate and refunds are made under orders of the competent authority after the defect liability period is over and subject to the certificate of the Engineers-in-Charge to the effect that no defects are noticed in execution.

## Slide 55
►Mode of Payments: Payments are made by cheques/ NEFT against budget provisions to avoid fraudulent payments. Taxes and royalties to be recovered are remitted to the proper authorities. The postings in the works abstract and register of works are to be checked to find out unnecessary expenditure, unauthorised execution of work, wrong adjustments and excess expenditure over budget provisions.

## Slide 56
Thank You